## Matrix-Package-D
Sr. No. |  |  | Main Gate | [11 empty] | LP Gate | [7 empty] | Phase 3 Gate/Jokatte Gate | [11 empty] | E2 Gate |  | PCR |  |  | Railway Sliding |  | Gargo Gate
| Type of Entry |  | Vehicle (Canopy) |  |  | Outdoor Area |  |  | Exe/VIP Pedestrian | Blue Collar Pedestrian |  |  |  |  | Vehicle ( Canopy) |  |  | Outdoor Area |  |  | Pedestrian |  | Vehicle (Canopy) |  |  | CISF Checking Gate |  | Outdoor Area |  |  | Exe/VIP Pedestrian | Blue Collar Pedestrian |  |  | Pedestrian & Gate |  | Pedestrian |  |  |  |  | Vehicle (Canopy)
| Gate |  | Entry | Exit | Status | Canopy | Parking & Roads | Status | Entry/Exit | Entry/Exit | Status | GF | 1F | Status | Entry | Exit | Status | Canopy | Parking & Roads | Status | Entry/Exit | Status | Entry | Exit | Status | Entry/Exit | Status | Canopy | Parking & Roads | Status | Entry/Exit | Entry/Exit | GF | Status | Entry/Exit | Status | Entry/Exit | CMD | Status |  | Status | Entry | Exit | Status | Total | G.Total Req. | BOQ Qty. | Diff
1 | Automatic Tyre Killer |  | 1 |  | Completed | [9 empty] | 1 |  | Completed | [5 empty] | 1 |  | Completed | [19 empty] | 3 | 3 | 3 | 0
2 | Manual Tyre Killer |  |  | 1 | Pending, installed & Removed | [10 empty] | 1 | Pending, installed & Removed | [6 empty] | 1 | Pending, installed & Removed | [19 empty] | 3 | 3 | 3 | 0
3 | UVSS |  | 2 |  | Completed | [9 empty] | 2 |  | Completed | [5 empty] | 2 |  | Completed | [19 empty] | 6 | 6 | 6 | 0
4 | Bollards |  | 4 | 4 | Completed | [9 empty] | 4 | 4 | Completed | [5 empty] | 4 | 4 | Completed | [19 empty] | 24 | 24 | 24 | 0
5 | Boom Barrier | 4m | 2 | 2 | Completed | [9 empty] | 2 | 2 | Completed | [5 empty] | 2 | 2 | Completed | 2 | Completed . Out of 04 nos we have installed 02 nos as per the site condition | [7 empty] | 2 | Completed | [8 empty] | 16 | 30 | 32 | -2
|  | 3m | 2 | 2 | Completed | [9 empty] | 2 | 2 | Completed | [5 empty] | 2 | 2 | Completed | [19 empty] | 12
|  | 6m | [39 empty] | 1 | 1 | Completed | 2
6 | Swing Barriers | N | [6 empty] | 2 | 6 | Completed | [9 empty] | 1 | Installation completed. | [8 empty] | 2 | 2 |  | Completed | 2 | Completed | 4 |  | Completed | [5 empty] | 19 | 19 | 19 | 0
7 |  | H | [6 empty] | 1 | 1 | Completed | [9 empty] | 1 | Installation completed. | [8 empty] | 1 | 1 |  | Completed | [10 empty] | 5 | 5 | 5 | 0
8 | Visitor Kiosks | [7 empty] | 1 | 2 | Pending, will install after site clerance & Dust free | [9 empty] | 1 | Pending | [8 empty] | 1 | 1 |  | 01 no Installed & 01 No Pending | [10 empty] | 6 | 6 | 6 | 0
9 | 32" Overhead Display | [7 empty] | 3 | 6 | Completed | [9 empty] | 2 | Completed | [8 empty] | 3 | 3 |  | Completed | 2 | Pending,Site Clerance required | [8 empty] | 19 | 19 | 20 | -1
10 | Indoor Digital Displays | [7 empty] | 2 | 2 | Pending, will install after site clerance | [9 empty] | 1 | Completed | [8 empty] | 2 | 1 |  | Completed | [10 empty] | 8 | 8 | 8 | 0
11 | Outdoor Digital Displays | [5 empty] | 3 | Foundation Works Complered | [10 empty] | 2 | Completed | [8 empty] | 3 | Completed | [11 empty] | 1 |  | Foundation Works Completed | 9 | 9 | 9 | 0
12 | Video Wall (6 by 3) | [11 empty] | 1 | Completed | [30 empty] | 1 | 1 | 1 | 0
13 | Video Wall (2 by 3) | [36 empty] | 1 | Completed | [5 empty] | 1 | 1 | 1 | 0
14 | DFMD | [7 empty] | 2 | 6 | Completed | [9 empty] | 1 | Installation completed. | [8 empty] | 2 | 2 |  | Installation completed. | 2 | Pending, Civil works not completed | [8 empty] | 15 | 15 | 15 | 0
15 | Baggage Scanner | [7 empty] | 1 | 2 | Completed | [9 empty] | 1 | Installation completed. | [8 empty] | 1 | 2 |  | Installation completed. | 1 | Pending, Civil works not completed | [8 empty] | 8 | 8 | 8 | 0
16 | Frisking Booth | [7 empty] | 1 | 1 | Completed | [9 empty] | 1 | Pending | [8 empty] | 1 | 1 |  | Pending | [10 empty] | 5 | 5 | 5 | 0
17 | Visitor Kiosks | [7 empty] | 1 | 2 | Pending | [9 empty] | 1 | Pending | [8 empty] | 1 | 1 |  | Pending | [10 empty] | 6 | 6 | 6 | 0
18 | Long Range RFID Reader |  | 4 | 4 | Completed | [9 empty] | 4 | 4 | Completed | [5 empty] | 4 | 4 | Completed | 2 | Pending | [7 empty] | 2 | Pending | [5 empty] | 1 | 1 | Pending | 30 | 30 | 32 | -2
19 | Push Button for Boom Barrier |  | 4 | 4 | Completed | [9 empty] | 4 | 4 | Completed | [5 empty] | 4 | 4 | Completed | 2 | Pending | [7 empty] | 2 | Pending | [5 empty] | 1 | 1 | Pending | 30 | 30 | 32 | -2
20 | EM Locks | SLL | [9 empty] | 2 |  | Pending | [6 empty] | 1 | Pending | [8 empty] | 2 |  |  | Installation completed. | [10 empty] | 5 | 7 | 7 | 0
|  | DLL | [9 empty] | 1 | 1 | Pending | [30 empty] | 2
21 | Indoor Dome - 5 MP |  |  |  |  | 2 | 1 | Pending. Canopy works under progress |  |  |  | 34 | 35 | Completed | [6 empty] | 10 | Completed | [5 empty] | 1 | 2 | Completed |  |  | 23 | Completed | 4 | Pending, Civil works not completed | [5 empty] | 2 |  | Pending | 114 | 114 | 116 | -2
22 | Outdoor Fixed - 5 MP |  |  |  |  | 12 | 26 | Parking & Roads Completed, Canopy Inside pending |  |  |  | 7 |  | Completed |  |  |  | 11 |  | Pending | 1 | Installation completed. | [5 empty] | 14 | 9 | Completed |  |  | 3 | Completed | 2 | Pending, Civil works not completed |  |  |  | 16 | Completed | 6 |  | Pending | 107 | 107 | 115 | -8
23 | PTZ with IR - 2MP | [5 empty] | 2 | Completed | [20 empty] | 2 | Completed | [9 empty] | 2 | Completed |  |  |  | 6 | 6 | 10 | -4
24 | Panoramic - 180 - 20 MP |  |  |  |  | 1 |  | Pending |  |  |  | 2 |  | Pending |  |  |  | 1 |  | Pending | 1 | Pending | [5 empty] | 2 |  | Pending |  |  | 2 | Pending | [10 empty] | 9 | 9 | 11 | -2
25 | Panoramic - 360 - 20 MP, |  |  |  |  | 8 |  | Completed | [9 empty] | 2 |  | Completed | [7 empty] | 3 | 9 | Completed | [14 empty] | 22 | 22 | 22 | 0
26 | ANPR Cameras |  |  |  |  | 4 | 2 | Completed, Parking area pending due to civil works dependency | [9 empty] | 4 |  | Completed | [7 empty] | 4 | 4 | Completed | [11 empty] | 2 |  | Pending | 20 | 20 | 25 | -5
27 | Face recognition Cameras |  |  |  |  | 4 |  | Completed |  |  |  | 6 |  | Completed |  |  |  | 4 |  | Completed | 2 | Completed | [5 empty] | 4 |  | Completed |  |  | 3 | Completed | [7 empty] | 2 |  | Pending | 25 | 25 | 25 | 0
28 | IP Horn Speaker |  |  |  |  | 6 | 31 | Canopy pending, Roads & Parking completed |  |  |  | 2 |  | Completed |  |  |  | 5 |  | Pending | [7 empty] | 9 | 25 | Completed |  |  | 1 | Completed | 2 | Pending | [5 empty] | 5 |  | Pending | 86 | 86 | 87 | -1
29 | IP Ceiling Speaker |  |  |  |  | 2 |  | Completed |  |  |  | 28 | 28 | Completed | [6 empty] | 5 | Completed | [6 empty] | 2 | Completed |  |  | 12 | Completed | 1 | Pending | [5 empty] | 2 |  | Pending | 80 | 80 | 80 | 0
30 | Master & Local Control Desks (Microphones) | [43 empty] | 7 | 7 | 7 | 0
31 | Face recognition Readers | [7 empty] | 6 | 14 | Completed | [9 empty] | 4 | Completed | [8 empty] | 6 | 6 |  | Completed | 4 | Pending | 8 |  | Completed | [5 empty] | 48 | 48 | 48 | 0
32 | Smart Card Reader | [10 empty] | 3 | 1 | Pending | [6 empty] | 1 | Pending | [8 empty] | 2 |  |  | Completed | [10 empty] | 7 | 7 | 7 | 0
33 | QR Code Readers | [7 empty] | 6 | 14 | Completed | [9 empty] | 4 | Completed | [8 empty] | 6 | 6 |  | Completed | 4 | Pending | 8 |  | Completed | [5 empty] | 48 | 48 | 48 | 0
34 | Camera Poles | 4M | 2 | 2 | Completed |  | 21 | Completed | [6 empty] | 2 | 2 | Completed | [5 empty] | 2 | 2 | Completed |  |  |  | 25 | Completed | [9 empty] | 16 | Completed | 3 |  | Pending | 77 | 77 | 119 | 16
35 |  | 2.5M | 2 | 2 | Completed | [9 empty] | 2 | 2 | Completed | [5 empty] | 2 | 2 | Completed | [19 empty] | 12 | 12
36 |  | 2/1M | 2 | 2 | Completed | [9 empty] | 2 | 2 | Completed | [5 empty] | 2 | 2 | Completed | [16 empty] | 1 | 1 | Pending | 14 | 14
37 | Rack (12U) |  | 1 | 1 | Completed | [6 empty] | 3 | 6 | Completed |  |  |  | 2 |  | 01 No Completed & 01 no pending | 1 | Completed | 1 | 1 | Completed | [7 empty] | 1 | Completed | 1 | Pending | [5 empty] | 1 |  | Pending | 19 | 19 | 21 | -2
38 | Outdoor Junction Box | [5 empty] | 16 | Completed | [20 empty] | 17 | Completed | [9 empty] | 14 | Completed |  |  |  | 47 | 47 | 52 | -5
39 | Portable face readers (installation in buses) | [5 empty] | 20 | Pending | [36 empty] | 20 | 20 | 20 | 0
40 | Portable face readers (on gates) | [5 empty] | 4 | Pending | [36 empty] | 4 | 4 | 4 | 0
41 | 10 finger enrolment readers (for contract labour) | [8 empty] | 2 | Pending | [9 empty] | 1 | Pending | [9 empty] | 1 |  | Pending | [10 empty] | 4 | 4 | 4 | 0
42 | Indoor signages | [10 empty] | 10 | 6 | Completed | [6 empty] | 2 | Completed | [10 empty] | 10 | Completed | 2 | Pending | [8 empty] | 30 | 30 | 30 | 0
43 | Wireless Access Point | [27 empty] | 1 | Pending | [9 empty] | 1 | Completed |  |  |  | 2 | 2 | 2 | 0
44 | Video Confrencing Solution | [10 empty] | 2 |  | 01 No at Command center Building Completed, 01 No at Main gate Clerance required | [30 empty] | 2 | 2 | 2 | 0
45 | Smart Rack | [10 empty] | 1 |  | Completed | [30 empty] | 1 | 1 | 1 | 0
46 | DG Set | [10 empty] | 1 |  | Completed (Roof Pending) | [18 empty] | 1 | Completed (Roof Pending) | [10 empty] | 2 | 2 | 2 | 0